## Cutover Activities Checklist
Overview of Cutover Activities
The Cutover Playbook is a list of activities to be completed before, during, and after a planned cutover to successfully .It provides teams with an effective way to prepare for any possible risks and issues while migrating users due to changes or unexpected impacts.
Cutover Information
Date of Cutover:
Sites to be Cut Over:
UPtime Components Impacted: |  | [ABC] Service Desk, [ABC] Depot, Knowledge Management, End User Portal, [ABC] ServiceNow ([ABC] as an example)
Other: |  | English
Two Weeks Prior to Cutover
Cutover Activity |  |  |  |  | Complete | Assigned to | Confirmed By | Comments
Conduct final verification of wave requirements Requirements should be reviewed together by the project teams and tech teams. This includes the list of in activities, which service desk/phone number should be available for US users | [5 empty] | All
Check communications are ready for cutover invite Communications team should review communications for any wave specific considerations | [5 empty] | Comms
Send UPtime pilot users to ServiceNow, Modern Workplace, and DXC IT Comms Specific user names and emails should be provided to the ServiceNow practice to add to the UPtime pilot group. | [5 empty] | PMO / Transition
Compile list of “test” SSOs users These are the test users that are going to log into UPtime a week before GO LIVE - these test users should not be part of the 100 users
Identify system changes that are being made to support the transition Review every system that was changed to support the UPtime (UPtime Portal, ServiceNow, Boomi, AWS Connect, any 3rd party partners)
Identify support contacts There needs to be a support team online for the cutover to address any issues that arise. The following table should be filled out with the primary support contact and their back up. Primary support contacts need to be actively online and available before and after the cutover.
| Function | Primary Contact (Name & Contact Info) | Secondary Contact (Name & Contact Info) | Online Coverage Date and Time
Uptime Portal
ServiceNow
Boomi
PC Lifecycle
| Service Desk | Amazon -
Lead -
Knowledge Articles
In addition to the above teams, are there any additional support functions that need to be present during the cut over? If so, add the contacts to the table
Week of Cutover
Cutover Activity |  |  |  |  | Complete | Assigned to | Confirmed By | Comments
Verify service desk capacity can handle potential volumes increases The expected volume increase needs to be verified against actual service desk capabilities.
Verify Service Desk agents and Depot engineers are trained on new UPtime / DXCi ServiceNow processes Service Desk agents need to clearly understand what functionality is availalble in UPtime and all workarounds in case of exceptions. Knowledge articles need to be updated on these exceptions and service desk agents need to be trained on these updates
Verify master data related data has been shared with the ServiceNow team DXC IT team will need to provide the following master data related information to ServiceNow
| Master Data | Primary Contact DXC (Name & Phone) | Primary ServiceNow Contact (Name & Phone) | Completion Date and Time
| Assignment Groups | Manas Sharma
| Categories and Sub Categories | Manas Sharma, Karthik and Sonal
| Business Services | Manas Sharma
Pilot User Data Information
Asset Data for the 100 users need to be given to ServiceNow DXC IT will share transaction information to load into ServiceNow
Check the “out of hours” message on chat has the correct phone number The Out of Hours message should direct users to an active vendor's phone number.
Send War Room Meeting Invites & Teams Link The war room meeting link should be a Teams link to be used the day of cutover. The first checkpoint should be at least 30 minutes prior to service desk opening where teams give the final go/no go before sending end user communications.
Share cutover timeline The war room meeting link should be a teams link to be used the day of cutover. The first checkpoint should be at least 30 minutes prior to service desk opening where teams give the final go/no go before sending end user communications.
| Activtiy Description | GMT-5 (USA - Eastern Standard Time) | GMT (UK) | GMT+10.5 (India)
| Pilot invitations are sent (emails) | Nov 17 18:30 | Nov 17 23:30 | Nov 18 5:00
| UPtime Service Desk agents are in new system & ready | Nov 18 7:00 | Nov 18 12:00 | Nov 18 17:30
| War Room Bridge Opens | Nov 18 7:00 | Nov 18 12:00 | Nov 18 17:30
| Nov 18th Townhall starts | Nov 18 8:00 | Nov 18 13:00 | Nov 18 18:30
| Pilot user group in ServiceNow activated (Users can begin accessing UPtime) | Nov 18 8:30 (approx.) | Nov 18 13:30 (approx.) | Nov 18 18:30 (approx.)
UPtime Service Desk is Open
| Houston Depot starts their day | Nov 18 9:00 | Nov 18 14:00 | Nov 18 19:30
| First Check In | Nov 18 10:00 | Nov 18 15:00 | Nov 18 20:30
| Mid Day Check In | Nov 18 13:00 | Nov 18 18:00 | Nov 18 23:30
| End of Day Check In | Nov 18 18:00 | Nov 18 23:00 | Nov 19 4:30
| War Room Bridge Closes (Service Desk remains open) | Nov 18 20:00 | Nov 19 1:00 | Nov 19 6:30
Day Before Cutover
Cutover Activity |  |  |  |  | Complete | Assigned to | Confirmed By | Comments
Verify all tools are working and all agents can access the required tools and accounts Test individual accounts and access for every tool the agent uses (i.e., UPtime, ServiceNow). This includes agents from: A) Expert Service Desk B) Depot C) UPtime
Conduct a final confirmation on agent availability All agents expected for the cutover should confirm whether they will be in place for the cutover. Check for any scheduling errors, capacity need changes, or unexpected emergencies that may impact capacity to support expected volume increases
Confirm TBD evening post-cutover checks have been completed
Day of Cutover
Cutover Activity |  |  |  |  | Complete |  | Confirmed By | Comments